## Sheet1
Request for Proposal/Contracts - Estimated Timelines
| Oct. 26-30 | Nov. 2-6 | Nov. 9-13 | Nov. 16-20 | Nov. 23-27 * | Nov. 30 - Dec. 4 | Dec. 7-11 | Dec. 14-18 | Dec. 21-25* | Dec. 28 - Jan. 1* | Jan. 4-8* | Jan. 11-15 | Jan. 18-22 | Jan. 25-29 | Feb. 1-5 | Feb. 8-12 | Feb. 15-19 | Feb. 22-26 | Mar. 1-5 | Mar. 8-12 | Mar. 15-19 | Mar. 22-26 | Mar. 29 - Apr. 2 | Apr. 5-9 | Apr. 12-16 | Apr. 19-23 | April 26-30
Videography - Business & Line Drawing Meetings
Interim Contract: CMAS $250,000 Maximum | DGS Review & Approval |  | 38 Meetings @ $6,500 per meeting
RFP and final contract through 06/30/2022 |  | Create the RFP | Staff & Com Rev | Com. Rev/Vote | DGS/OLS Review and Approval | [5 empty] | RFP Posted** |  |  |  | Staff & Com Rev | Com. Rev/Award | 5 day Protest | Contract Signed |  | DGS Review and Approval
Videography - Outreach and Public Hearings
RFP and final contract through 06/30/2022 |  |  | Create the RFP | Staff & Com Rev | Com. Rev/Vote | DGS/OLS Review and Approval | [5 empty] | RFP Posted** |  |  |  | Staff & Com Rev | Com. Rev/Award | 5 day Protest | Contract Signed |  | DGS Review and Approval
Line Drawer |  | Create the RFP | Staff & Com Rev | Com. Rev/Vote | DGS/OLS Review and Approval | [5 empty] | RFP Posted** |  |  |  | Staff & Com Rev | Com. Rev/Award | 5 day Protest | Contract Signed |  | DGS Review and Approval
Data Management and Data Mining |  | Create the RFP | Staff & Com Rev | Com. Rev/Vote | DGS/OLS Review and Approval | [5 empty] | RFP Posted** |  |  |  | Staff & Com Rev | Com. Rev/Award | 5 day Protest | Contract Signed |  | DGS Review and Approval
Voting Right Act Counsel |  | Create the RFP | Staff & Com Rev | Com. Rev/Vote | DGS/OLS Review and Approval | [5 empty] | RFP Posted** |  |  |  | Staff & Com Rev | Com. Rev/Award | 5 day Protest | Contract Signed |  | DGS Review and Approval
Racially Polarized Voting Consultant |  | Create the RFP | Staff & Com Rev | Com. Rev/Vote | DGS/OLS Review and Approval | [5 empty] | RFP Posted** |  |  |  | Staff & Com Rev | Com. Rev/Award | 5 day Protest | Contract Signed |  | DGS Review and Approval
Outside Counsel for Litigation *** | [6 empty] | Create the RFP | Staff & Com Rev | Com. Rev/Vote | DGS/OLS Review and Approval |  | RFP Posted** |  |  |  | Staff & Com Rev | Com. Rev/Award | Contract Signed |  | DGS Review and Approval
* The Department of General Service's Office of Legal Services requires at least a 30 day review and approval period. The time period
shown is 42 days because of the Thanksgiving, Christmas and New Year's holiday period which typically increases the length of time
for the review and approval process. This time may be shorter than shown but it is unlikely that I would be less than 30 days.
** The minimum posting period for an RFP is 10 days. The maximum is "until filled". Typically, major contracts are for at least 30 days.
Thirty days allows the contractor enough time to research and complete their proposal.
*** The contracting requirements for legal counsel differ from general contracting requirements.