## Sheet1
|  |  | 2020 | [13 empty] | 2021 | [51 empty] | 2022
|  |  | 4Q | [13 empty] | 1Q | [12 empty] | 2Q | [12 empty] | 3Q | [12 empty] | 4Q | [12 empty] | 1Q | [12 empty] | 2Q
|  |  | October |  |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June
|  |  | 27 Sep - 3 Oct | 4 Oct - 9 Oct | 10 Oct - 16 Oct | 17 Oct - 23 Oct | 24 Oct- 30 Oct | 31 Oct - 7 Nov | 8 Nov - 14 Nov | 15 Nov - 21 Nov | 22 Nov - 28 Nov | 29 Nov - 5 Dec | 6 Dec - 12 Dec | 13 Dec - 19 Dec | 20 Dec - 26 Dec | 27 Dec - 2 Jan | 3 Jan - 9 Jan | 10 Jan - 16 Jan | 17 Jan - 23 Jan | 24 Jan - 30 Jan | 31 Jan - 6 Feb | 7 Feb - 13 Feb | 14 Feb - 20 Feb | 21 Feb - 27 Feb | 28 Feb - 6 Mar | 7 Mar - 13 Mar | 14 Mar - 20 Mar | 21 Mar - 27 Mar | 28 Mar - 3 Apr | 4 Apr - 10 Apr | 11 Apr - 17 Apr | 18 Apr - 24 Apr | 25 Apr - 1 May | 2 May - 8 May | 9 May - 15 May | 16 May - 22 May | 23 May - 29 May | 30 May - 5 Jun | 6 Jun - 12 Jun | 13 Jun - 19 Jun | 20 Jun - 26 Jun | 27 Jun - 3 Jul | 4 Jul - 10 Jul | 11 Jul - 17 Jul | 18 Jul - 24 Jul | 25 Jul - 31 Jul | 1 Aug - 7 Aug | 8 Aug - 14 Aug | 15 Aug - 21 Aug | 22 Aug - 28 Aug | 29 Aug - 4 Sep | 5 Sep - 11 Sep | 12 Sep - 18 Sep | 19 Sep - 25 Sep | 26 Sep - 2 Oct | 3 Oct - 9 Oct | 10 Oct - 16 Oct | 17 Oct - 23 Oct | 24 Oct - 30 Oct | 31 Oct - 6 Nov | 7 Nov - 13 Nov | 14 Nov - 20 Nov | 21 Nov - 27 Nov | 28 Nov - 4 Dec | 5 Dec - 11 Dec | 12 Dec - 18 Dec | 19 Dec - 25 Dec | 26 Dec - 1 Jan | 2 Jan - 8 Jan | 9 Jan - 15 Jan | 16 Jan - 22 Jan | 23 Jan - 29 Jan | 30 Jan - 5 Feb | 6 Feb - 12 Feb | 13 Feb - 19 Feb | 20 Feb - 26 Feb | 27 Feb - 5 Mar | 6 Mar - 12 Mar | 13 Mar - 19 Mar | 20 Mar - 26 Mar | 27 Mar - 2 Apr | 3 Apr - 9 Apr | 10 Apr - 16 Apr | 17 Apr - 23 Apr | 24 Apr - 30 Apr | 1 May - 7 May | 8 May - 14 May | 15 May - 21 May | 22 May - 28 May | 29 May - 4 June | 5 June - 11 June | 12 June - 18 June | 19 June - 25 June | 26 June - 2 July
TASK | START | END
Recruitment & Selection of Commission
Public Information Campaign
Initial Applications Due | 2019-06-10 | 2019-08-19
Supplemental Applications Due | 2019-08-21 | 2019-10-13
Interviews | 2020-03-02 | 2020-04-23
Legislative Review | 2020-05-15 | 2020-06-30
Random Draw of First Eight | 2020-07-02 | 2020-07-02
First Eight Choose Final Six | 2020-08-04 | 2020-08-15
Commission Orientation and Operationalization
Commission Orientation | 2020-07-21 | 2020-09-04
Develop Initial Staffing & Procurement Plans | 2020-08-26 | 2020-12-31
Recruit Core Staff | 2020-08-26 | 2020-11-30
Develop budget | 2020-11-01 | 2020-11-30
Onboard Core Staff | 2020-10-01 | 2020-12-31
Recruit additional staff | 2021-01-01 | 2021-03-31
VRA Training | 2021-01-26 | 2021-01-28
Estab. Interim Video Contract for Bus.& Line Drwng Mtgs |  | 2020-11-07
Estab. Video Contract for Bus.& Line Drwng Mtgs | 2020-11-01 | 2021-04-02
Estab. Video Contract for Outreach & Public Hearings | 2020-11-09 | 2021-04-02
Estab. Data Mgmt/Data Mining Contract | 2020-11-01 | 2021-03-06
Public Education
Identify Partners | 2020-10-15 | 2021-03-31
Develop Education Plan | 2020-11-01 | 2021-02-15
Develop Education Materials | 2020-11-01 | 2021-02-15
Production and Distribution of Materials | 2020-12-15 | 2021-03-31
Develop and produce first video | 2021-01-02 | 2/28 21
Additional video production | 2021-03-01 | 2021-03-31
Organize Education Sessions | 2021-01-02 | 2021-05-31
Hold Education Sessions | 2021-02-01 | 2021-05-31
Social Media Ad Campaign & Traditional Media Presence | 2021-02-01 | 2021-12-31
Collect and Analyze RPV Data
Estab. VRA Counsel contract | 2020-11-01 | 2021-03-27
VRA Counsel starts | 2021-04-01 | 2021-04-01
Estab. VRA Consultant contract | 2020-11-01 | 2021-04-02
VRA Consultant starts | 2021-04-01 | 2021-04-02
Estab. RPV Analyst contracts | 2020-11-01 | 2021-04-02
Prepare initial RPV Overview of the state | 2021-01-02 | 2021-02-17
RPV Analyst starts | 2021-04-01 | 2021-04-01
Collect Data | 2021-01-02 | 2021-04-30
Analyze Data | 2021-01-15 | 2021-06-30
Collect Communities of Interest Input
Statewide Database Builds CoI Tool |  | 2021-01-31
Develop CoI Input Plan | 2021-01-02 | 2021-03-31
Organize CoI Input Sessions | 2021-04-01 | 2021-05-31
Host CoI Input Sessions | 2021-06-01 | 2021-09-30
Organize CoI Input Session Inputs | 2021-06-01 | 2021-09-30
Analyze CoI Input Session Inputs | 2021-06-01 | 2021-09-30
Data Management
Task 1
Task 2
Complete development of data mgmt system | 2021-02-01 | 2021-02-28
Complete development of staffing plan | 2021-02-01 | 2021-02-28
Determine relationship with USDR | 2021-02-01 | 2021-02-28
Develop duty statement for Data Manager | 2021-02-01 | 2021-02-28
Develop RfI for Data Analyst | 2021-02-01 | 2021-02-28
Recruit Data Manager and Data Analyst | 2021-02-01 | 2021-02-28
Post openings | 2021-02-01 | 2021-02-28
Review applications | 2021-03-01 | 2021-03-31
Recommend & approve hires | 2021-03-01 | 2021-03-31
Data Manager, Data Analyst start work | 2021-03-01 | 2021-03-31
Obtain licenses for Data Management System | 2021-03-01 | 2021-03-31
Configure Data Management System | 2021-03-01 | 2021-03-31
Develop system for manual review and input of non-CoI Tool documents | 2021-03-01 | 2021-03-31
Hire Temporary Staff | 2021-04-01 | 2021-04-30
Develop duty statement | 2021-04-01 | 2021-04-30
Post & distribute duty statement | 2021-04-01 | 2021-04-30
Interview and select temporary staff | 2021-04-01 | 2021-04-30
Temporary staff start | 2021-04-01 | 2021-04-30
Census Data
Public Information Campaign | 2019-11-01 | 2020-09-30
Data Collection | 2020-04-01 | 2020-10-15
Data Processing | 2020-04-06 | 2021-03-05
Deliver Apportionment Counts to President | 2021-03-31 | 2021-03-31
ACS Data Release | 2021-02-02 | 2021-02-06
PL94-171 Data Release | 2021-09-30 | 2021-09-30
Statewide Database Builds Redistricting Database | 2021-10-01 | 2021-10-30
Commission Receives Redistricting Database | 2021-10-31 | 2021-10-31
Map Drawing
Estab. Line Drawer Contract | 2020-11-01 | 2021-02-28
Line Drawers start | 2021-03-15 | 2021-03-15
Training for Commissioners
Organize Map-Drawing Sessions | 2021-10-01 | 2021-10-31
Hold Map-Drawing Sessions | 2021-11-01 | 2021-12-15
Develop VRA Districts | 2021-11-01 | 2021-11-30
Develop full draft maps | 2021-11-01 | 2021-12-15
Release Draft Maps | 2021-12-15 | 2021-12-15
Draft Reports | 2021-12-15 | 2021-12-31
Revise draft maps | 2022-01-01 | 2022-01-15
Finalize Reports | 2022-01-16 | 2022-01-31
Review Final Maps | 2022-01-21 | 2022-01-28
Approve & Deliver Final Maps | 2022-01-29 | 2022-01-31
Litigation
Estab. Outside Counsel contract | 2020-12-07 | 2021-02-28
Outside Counsel starts | 2021-03-07 | 2021-03-07
Election Administration
SecState delivers Commission maps to County Registrars
Revision of precinct boundaries
Deadline for finalization of precincts | 2022-02-11 | 2022-02-11
Candidate Filing Period | 2022-02-15 | 2022-03-12
Primary | 2022-06-07 | 2022-06-07
Formulas:
END = [START]+70
START = [END, row above]+1
START = [START, row above]+5