## Sheet1
|  |  | 2020 | [13 empty] | 2021
|  |  | 4Q | [13 empty] | 1Q | [12 empty] | 2Q | [12 empty] | 3Q | [12 empty] | 4Q
|  |  | October |  |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December
|  |  | 27 Sep - 3 Oct | 4 Oct - 9 Oct | 10 Oct - 16 Oct | 17 Oct - 23 Oct | 24 Oct- 30 Oct | 31 Oct - 7 Nov | 8 Nov - 14 Nov | 15 Nov - 21 Nov | 22 Nov - 28 Nov | 29 Nov - 5 Dec | 6 Dec - 12 Dec | 13 Dec - 19 Dec | 20 Dec - 26 Dec | 27 Dec - 2 Jan | 3 Jan - 9 Jan | 10 Jan - 16 Jan | 17 Jan - 23 Jan | 24 Jan - 30 Jan | 31 Jan - 6 Feb | 7 Feb - 13 Feb | 14 Feb - 20 Feb | 21 Feb - 27 Feb | 28 Feb - 6 Mar | 7 Mar - 13 Mar | 14 Mar - 20 Mar | 21 Mar - 27 Mar | 28 Mar - 3 Apr | 4 Apr - 10 Apr | 11 Apr - 17 Apr | 18 Apr - 24 Apr | 25 Apr - 1 May | 2 May - 8 May | 9 May - 15 May | 16 May - 22 May | 23 May - 29 May | 30 May - 5 Jun | 6 Jun - 12 Jun | 13 Jun - 19 Jun | 20 Jun - 26 Jun | 27 Jun - 3 Jul | 4 Jul - 10 Jul | 11 Jul - 17 Jul | 18 Jul - 24 Jul | 25 Jul - 31 Jul | 1 Aug - 7 Aug | 8 Aug - 14 Aug | 15 Aug - 21 Aug | 22 Aug - 28 Aug | 29 Aug - 4 Sep | 5 Sep - 11 Sep | 12 Sep - 18 Sep | 19 Sep - 25 Sep | 26 Sep - 2 Oct | 3 Oct - 9 Oct | 10 Oct - 16 Oct | 17 Oct - 23 Oct | 24 Oct - 30 Oct | 31 Oct - 6 Nov | 7 Nov - 13 Nov | 14 Nov - 20 Nov | 21 Nov - 27 Nov | 28 Nov - 4 Dec | 5 Dec - 11 Dec | 12 Dec - 18 Dec | 19 Dec - 25 Dec | 26 Dec - 1 Jan
TASK | START | END
Recruitment & Selection of Commission
Public Information Campaign
Initial Applications Due | 2019-06-10 | 2019-08-19
Supplemental Applications Due | 2019-08-21 | 2019-10-13
Interviews | 2020-03-02 | 2020-04-23
Legislative Review | 2020-05-15 | 2020-06-30
Random Draw of First Eight | 2020-07-02 | 2020-07-02
First Eight Choose Final Six | 2020-08-04 | 2020-08-15
Commission Orientation and Operationalization
Commission Orientation | 2020-07-21 | 2020-09-04
Develop Initial Staffing & Procurement Plans | 2020-08-26 | 2020-12-31
Recruit Core Staff | 2020-08-26 | 2020-11-30
Develop budget | 2020-11-01 | 2020-11-30
Onboard Core Staff | 2020-10-01 | 2020-12-31
Recruit additional staff | 2021-01-01 | 2021-03-31
Estab. Interim Video Contract for Bus.& Line Drwng Mtgs |  | 2020-11-07
Estab. Video Contract for Bus.& Line Drwng Mtgs | 2020-11-01 | 2021-04-02
Estab. Video Contract for Outreach & Public Hearings | 2020-11-09 | 2021-04-02
Estab. Data Mgmt/Data Mining Contract | 2020-11-01 | 2021-03-06
Public Education
Identify Partners | 2020-10-15 | 2021-01-23
Develop Education Plan | 2020-11-01 | 2020-12-31
Develop Education Materials | 2020-11-01 | 2021-01-31
Production and Distribution of Materials | 2020-12-15 | 2021-02-28
Training of Trainers | 2021-01-02 | 2021-01-31
Organize Education Sessions | 2020-11-06 | 2021-02-14
Host Education Sessions | 2021-01-17 | 2021-03-27
Task 5
Collect and Analyze RPV Data
Estab. VRA Counsel contract | 2020-11-01 | 2021-03-27
VRA Counsel starts | 2021-04-01 | 2021-04-01
Estab. VRA Consultant contract | 2020-11-01 | 2021-04-02
VRA Consultant starts | 2021-04-01 | 2021-04-02
Estab. RPV Analyst contracts | 2020-11-01 | 2021-04-02
Prepare initial RPV Overview of the state | 2021-01-02 | 2021-03-27
RPV Analyst starts | 2021-04-01 | 2021-04-01
Collect Data | 2021-01-02 | 2021-04-30
Analyze Data | 2021-01-15 | 2021-06-30
Task 4
Task 5
Collect Communities of Interest Input
Statewide Database Builds CoI Tool |  | 2021-01-31
Develop CoI Input Plan | 2021-01-02 | 2021-01-30
Organize CoI Input Sessions | 2021-01-31 | 2021-04-01
Host CoI Input Sessions | 2021-04-01 | 2021-05-01
Organize CoI Input Session Inputs | 2021-04-01 | 2021-06-30
Analyze CoI Input Session Inputs | 2021-04-01 | 2021-06-30
Census Data
Public Information Campaign | 2019-11-01 | 2020-09-30
Data Collection | 2020-04-01 | 2020-10-15
Data Processing | 2020-04-06 | 2020-12-31
Deliver Apportionment Counts to President | 2020-12-31 | 2020-12-31
ACS Data Release | 2021-02-02 | 2021-02-06
PL94-171 Data Release | 2021-03-31 | 2021-03-31
Statewide Database Builds Redistricting Database | 2021-04-01 | 2021-05-01
Map Drawing
Estab. Line Drawer Contract | 2020-11-01 | 2021-04-02
Line Drawers start | 2021-04-01 | 2021-04-01
Training for Commissioners | 2021-01-04 | 2021-01-29
Organize Map-Drawing Sessions | 2021-04-01 | 2021-06-30
Hold Map-Drawing Sessions | 2021-05-01 | 2021-06-30
Develop VRA Districts | 2021-05-01 | 2021-05-31
Develop full draft maps | 2021-05-01 | 2021-06-30
Release Draft Maps | 2021-07-01 | 2021-07-01
Draft Reports | 2021-07-01 | 2021-07-15
Revise draft maps | 2021-07-15 | 2021-08-08
Finalize Reports | 2021-08-08 | 2021-08-14
Review Final Maps | 2021-08-08 | 2021-08-14
Approve & Deliver Final Maps | 2021-08-14 | 2021-08-15
Litigation
Estab. Outside Counsel contract | 2020-12-07 | 2021-02-28
Outside Counsel starts | 2021-03-07 | 2021-03-07
Task 3 | date | date
Task 4 | date | date
Task 5 | date | date
Formulas:
END = [START]+70
START = [END, row above]+1
START = [START, row above]+5